# Operating Targets for 2003/4

Each target must be able to be readily assessed (achieved, not achieved, partly achieved).

|  | Target | Champion | Progress report |
| --- | --- | --- | --- |
|  | Overall Strategic |  |  |
| 1 | Secure research funds from one or more FP6 Integrated Projects | Mike Hulme/ John Schellnhuber/ Alex Haxeltine | The flagship bid into the 1st call of FP6 (AMS-Europe) was not successful. I do not yet know whether Tyndall’s, more minor, roles in a few other bids were successful. We are taking a leading role in two 2nd call bids (MATISSE and ProMed), outcomes known next summer. The 3rd call will be made early in 2004. |
| 2 | Complete strategy for a long-term strategic alliance with the Potsdam Institute for Climate Impact Research (PIK) | John Schellnhuber/ Mike Hulme | We have agreed a series of documents outlining the scope and purpose of the strategic alliance, and the alliance itself has been welcomed at senior levels in both UK and Germany. A first Tyndall-PIK Summit meeting was held at UEA in August – involving about 16 scientists and this laid out a number of areas for future scientific collaboration and exchange. A second Summit will take place in the New Year in Potsdam. No additional resources for the alliance – other than a small British Council grant – have been secured. |
| 3 | Align the Tyndall Centre with the new national Energy Research Centre | John Schellnhuber/ Mike Hulme/ Brian Launder/ John Shepherd | This is in progress and a document outlining the Tyndall position has been circulated. Three bids are being submitted to the research councils in November and the Tyndall Centre is following the progress of all three. There is a recognition in the community that a close alignment between the two Centres is important. |
| 4 | Undertake appropriate financial planning to ensure the Tyndall Centre continues to function effectively in 2005 (the last year of the initial phase of core funding) | Samantha Jones | The core Tyndall Centre grant from NERC, EPSRC and ESRC runs from October 2000 to September 2005. The five year budget for this grant has been designed to ensure that there is appropriate funding throughout its duration for the Centre’s core research, external communication and training activities, and for core staff and associated support costs. This five year budget is updated as necessary, to reflect changes and to ensure that actual expenditure remains as close as possible to the total budget of £10m, which is cash-limited. More detailed financial planning for the core grant is undertaken by the Research Councils’ financial year, April to March. Estimates for financial years 2004-5 and 2005-6 will be prepared in December 2003 and December 2004 respectively, and submitted to the Research Councils for approval. The Tyndall Centre’s second largest grant is from the DTI and this is due to end in December 2003. Negotiations are underway with the DTI concerning contract renewal, but are proceeding more slowly than we would have wished. Expenditure on all Centre grants is monitored through regular progress reports and adjustments made to budgets as necessary. |
|  | Target | Champion | Progress report |
| 5 | Run a COP9 side event | Neil Adger/ Alex Haxeltine |  |
| 6 | Convene two further Tyndall Symposia addressing strategic issues | Vanessa McGregor/ Laura Middleton/ Mike Hulme/ John Schellnhuber | An ECF Conference on the EU Biofuels Directive was organised and convened by the Tyndall Centre (and jointly funded with the ECF) in September 2003. This was attended by 50 representatives from European research, policy and industrial organisations. A Tyndall Symposium is being organised for January 2004 in Cambridge on macro-engineering options for climate change management, jointly funded with the Cambridge-MIT Institute. Two further Symposia are being planned for summer 2004 on energy-economic modelling and on perceptions of dangerous climate change. |
| 7 | Hold two further Tyndall ‘showcase’ events in London for government stakeholders | Elaine Jones/ Mike Hulme/ | No progress on this target yet. |
|  | Management |  |  |
| 1 | Agree detailed timetable/objectives for evaluation of the Tyndall Centre in winter/spring 2004, and ensure the Centre’s contribution to the necessary practical arrangements for the review | Samantha Jones/ John Schellnhuber/ Mike Hulme/ Brian Launder/ John Shepherd | It has been agreed with the Research Councils that there will be an internal management audit of the Tyndall Centre, which is likely to occur in autumn 2003. This will be undertaken by UEA’s internal audit team. The results of this will feed in to the Research Councils’ evaluation. The evaluation will include a site visit and the dates have been set for 19-23 April 2004. The Research Councils are due to consult us in late August 2003 about the rest of the timetable and terms of reference for the evaluation. We will need to respond by the end of September. |
| 2 | Conduct the second Annual Assessment Panel (AAP) review of Tyndall Centre activities | Samantha Jones | The second AAP meeting has been arranged for 26 November 2003. In the coming months, consideration will be given to the detailed structure and working of the review, which Tyndall Centre staff should be involved and the supporting material required. |
| 3 | Organise the third Tyndall Assembly with wide participation from Tyndall researchers | Vanessa McGregor/ Joan Hutchings |  |
| 4 | Complete round 3 funding allocation and contracting | Samantha Jones | There were 26 round 3 full proposals. Decisions have been made on most of these and feedback provided to applicants. Four proposals are still at provisional stage, and one was not pursued. Contracts have been issued for 19 of the remaining 21 proposals; for the other two, various queries need to be settled before proceeding to the contract stage. 16 of the 19 contracts issued have been accepted by the lead institutions. Most of these 19 projects are now underway, with the others to commence in September or October 2003. The Centre Manager will continue to monitor progress on the outstanding proposals. |
|  | Target | Champion | Progress report |
| 5 | Ensure smooth re-location of Tyndall HQ into the new Zuckerman Institute for Connective Environmental Research (ZICER) building at UEA | Samantha Jones | The re-location took place in July 2003. A number of practical issues were identified which would need resolving in order to ensure smooth transfer to ZICER. These were handled at officer level, and through a ZICER Transition Committee consisting of the ZICER Director and staff from research units re-locating to ZICER. Some of these issues were dealt with successfully, including the significant task of moving staff, their belongings and communal items to ZICER. However, due to various obstacles and despite best efforts, some practical issues remain unresolved. This led to some teething problems in the new building, and we are still working to clear these up. |
|  | Research Outcomes |  |  |
| 1 | Ensure all round 1 and round 2 projects report interim findings or final results through either a Tyndall Working Paper, Briefing Note or final project report | Asher Minns |  |
| 2 | For each research theme, ensure ten papers of Tyndall value-added research findings submitted to peer-reviewed publications (research wholly or predominantly funded by the Tyndall Centre) | Research Theme Managers/ Research Project Lead Investigators |  |
| 3 | All research projects should show at least one example of efforts to communicate to a wider audience, either through a media interview or by participating in an outreach event | Asher Minns/ Research Theme Managers |  |
| 4 | First implementation of the Tyndall Community Integrated Assessment Model (CIAM^n) prototype | Jonathan Kohler |  |
| 5 | Progress and refine Tyndall methodology for integrated assessment of pathways to UK decarbonisation | Nick Jenkins/ Simon Shackley |  |
| 6 | Develop a coherent synthesis of findings on Tyndall adaptation research for publication | Neil Adger/ Nigel Arnell |  |
| 7 | Publish an expanded written version of the strategy for the Tyndall regional coastal simulator | Andrew Watkinson/ Mikis Tsimplis |  |
|  | Outreach and Training |  |  |
| 1 | Develop, write and distribute a new communication strategy for the Tyndall Centre | Asher Minns |  |
|  | Target | Champion | Progress report |
| 2 | Explore ways to further engage the Regional Centres with external communication activities and assess the need to promote the Regional Centres to their host Institutions | Asher Minns |  |
| 3 | Showcase Tyndall Centre research at three major national stakeholder conferences | Elaine Jones/ Asher Minns |  |
| 4 | Organise two or more business briefings (eg half-day seminars) on climate change topics | Elaine Jones |  |
| 5 | Ensure two further visiting fellowships commence during the year | Cheryl Gardner |  |
| 6 | Complete two or more major training activities during the year | Laura Middleton |  |
| 7 | Successfully contribute to the Third Sustainability Days events and ZICER opening | Mike Hulme/ Neil Adger/ Elaine Jones | These contributions were made and the Tyndall Centre was in the lead for many of them – the sustainable energy seminar, the justice and equity workshop, and the ECF biofuels conference and the opening itself. Many participants have commented on how impressive the opening was and how stimulating the various events were. These events received widespread regional publicity and brought many senior international scientists and policy-makers into contact with the Tyndall Centre. |

V/SRJ

26.08.03

c:\my documents\reports & workplans\targets_ 2003-4

Extra text for overall strategic 4:

The contract for this grant actually ends on 31 December 2005. This will provide a 3 month period after 30 September for dealing with outstanding financial claims.  However we hope that, following the Research Councils’ review of the Tyndall Centre, core funding for a second will be provided. A decision on this should be made in good time before the end of the phase 1 contract (see management target 1 below).   It will also be an aim of negotiations on any phase 2 contract to ensure this runs on continuously from phase 1 contract, to allow seamless financial planning.

The Centre will continue to apply for external funding, in line with its strategy of seeking matching funds during the initial core funding period.